## Project Information
PROJECT BASIC INFORMATION
Project Name | Huntd
Name of Product | The best app for hiring web3 developers.
| Links | Test plan | Permission table | RTM
|  | Jira | TestRail WEB | TestRail Mobile
Product Description | Huntd is a comprehensive job search and application tracking app designed to assist job seekers in their quest for employment. With its user-friendly interface and powerful features, this app is essential for individuals actively seeking job opportunities.
Project Description | Mission of the project | Conduct testing to verify the quality of the web and mobile application.
Ensure the application is released without defects.
| Project output product | Test Summary report and Defects evaluation
| Project Type | Testing
Project Duration | Start date | 2025-12-19 | End date | 2025-12-24
Test Objectives | The test objectives are the functionality of the web version and mobile version of the “Huntd”. The project focuses on the possibility to interact with the main objects of the website and app.
For Website the main objectives are: - Verification of main pages and core user flows - Validation of candidate search, profiles, and filters - Verification of registration, authentication, and profile management - Validation of chat functionality and access rules - Verification of Web3 companies, jobs, and application flow
For Mobile the main objectives are: - Verification of implemented MVP features - Validation of authentication, chat, and profile settings - Identification of mobile-specific defects

## Test Summary
Execution Rate for Huntd Web app | [6 empty] | Execution Rate for Huntd mobile app
Executed test cases |  | 115 | 100% |  |  |  | Executed test cases |  | 80 | 100%
Passed |  | 105 | 91.3% |  |  |  | Passed |  | 73 | 91.25%
Failed |  | 10 | 8.696% |  |  |  | Failed |  | 6 | 7.5%
[7 empty] | Skipped |  | 1 | 1.37%
Huntd Web bugs by Priority | [6 empty] | Huntd Mobile app bugs by Priority
Critical |  | 0 | 0% |  |  |  | Critical |  | 0 | 0%
High |  | 0 | 0% |  |  |  | High |  | 1 | 10%
Medium |  | 10 | 100% |  |  |  | Medium |  | 5 | 50%
Low |  | 0 | 0% |  |  |  | Low |  | 0 | 0%
Web features | [6 empty] | Mobile features
No. | Features | Tests | Passed |  | Failed |  | No. | Features | Tests | Passed |  | Failed
1 | Main page For companies | 4 | 4 | 100% | 0 | 0% | 1 | Sing In | 7 | 6 | 85.71% | 0 | 0%
2 | Main page for engineers | 9 | 9 | 100% | 0 | 0% | 2 | Create Account | 7 | 7 | 100% | 0 | 0%
3 | Candidates list | 1 | 1 | 100% | 0 | 0% | 3 | Forgot Password | 1 | 1 | 100% | 0 | 0%
4 | Candidates filters | 8 | 8 | 100% | 0 | 0% | 4 | Botton Navigation Panel | 2 | 2 | 100% | 0 | 0%
5 | Candidates | 3 | 3 | 100% | 0 | 0% | 5 | Chat | 5 | 5 | 100% | 0 | 0%
6 | Candidate Profile | 2 | 1 | 50% | 1 | 50% | 6 | Profile | 4 | 4 | 100% | 0 | 0%
7 | Sign up | 6 | 6 | 100% | 0 | 0% | 7 | Edit Candidate Profile - Role | 11 | 9 | 81.82% | 2 | 18.18%
8 | Sign Up as a Recruiter | 12 | 12 | 100% | 0 | 0% | 8 | Edit Candidate Profile - Expectations | 12 | 8 | 66.67% | 4 | 33.33%
9 | Sign Up as a Candidate - Role section | 2 | 2 | 100% | 0 | 0% | 9 | Candidate Profile | 5 | 5 | 100% | 0 | 0%
10 | Sign Up as a Candidate - Expextation section | 7 | 6 | 85.71% | 1 | 14.29% | 10 | Preview Candidate's Profile | 4 | 4 | 100% | 0 | 0%
11 | Sing Up Candidate - Expiriesne section | 2 | 2 | 100% | 0 | 0% | 11 | Edit Recruiter Profile - Company Details | 4 | 4 | 100% | 0 | 0%
12 | Sing Up Candidate - Bio section | 2 | 2 | 100% | 0 | 0% | 12 | Recruter Profile - Preview Profile | 2 | 2 | 100% | 0 | 0%
13 | Sing Up Candidate - Contact Information section | 4 | 4 | 100% | 0 | 0% | 13 | Recruter Profile | 5 | 5 | 100% | 0 | 0%
14 | Sign in | 2 | 2 | 100% | 0 | 0% | 14 | Preview Recruter's Profile | 3 | 3 | 100% | 0 | 0%
15 | Chat | 12 | 9 | 75% | 3 | 25% | 15 | Contacts | 4 | 4 | 100% | 0 | 0%
16 | Profile | 12 | 11 | 91.67% | 1 | 8.333% | 16 | Preferences | 3 | 3 | 100% | 0 | 0%
17 | Footer | 15 | 12 | 80% | 3 | 20% |  | Latest (Coverage) | 79 | 72 | 91.14% | 6 | 7.595%
18 | Web3 Companies & Jobs | 12 | 11 | 91.67% | 1 | 8.333%
| Latest (Coverage) | 115 | 105 | 91.3% | 10 | 8.696%